## 项目
Gantt Chart
Learner Analytics
Activities | Period
| Sprint 1 (9.15-->9.26) |  |  | Sprint 2 (9.27-->10.17) |  |  |  | Sprint 3 (10.18-->11.04) |  | Sprint 4 (11.05-->11.21) |  |  | Sprint 5 (11.22-->12.02)
| 9.18 |  | 9.25 | 10.02 |  | 10.09 | 10.16 | 10.23 | 10.3 | 11.06 | 11.13 | 11.2 | 11.27 | 11.3 | 12.02
Sprint 1
Set up Cybera
Gannt Chart
User Stories
UML Diagram
Project Management
Storyboard
Prototype Design
IS1
Sprint 2
Upload csv file
Populate database
Update user stories
Update Gantt Chart
As1
IS2
IS3
Sprint 3
IS4
IS5
IS6
IS7
Sprint 4
IS8
IS9
Update UI
UI Testing
Sprint 5
As2
UI Updating
Demo Screen cast
Client Decomentation
Presenatation
Programmers |  | Omar
Wei Song
Hong Chen
Sprint 1:
Planning:
Design document(User stories), UML diagram, UI design graph/Story boarding, Gantt Chart, Project Overview
Task Assignment:
Omar: Setting up Cybera server and Gantt Chart
Hong: User Stories, UML diagram and planning
Wei: UI and prototype Design and Storyboard
Sprint 2:
Planning:
Finish User Stories IS1, IS2, IS4, AS1 The prototype should allow user(admin) to upload data into database and allow instructor to use some basic features including looking at student list, student performance and individual student profile page with basic information like grade
Task Assignment(tentative):
Omar: User Stories AS1, upload CSV file into Mysql and populate the database
Hong: User Stories IS1, IS2, IS3, set up database connection to backend with PHP
Wei: UI Design for the front end and help finish the user stories for this sprint
Sprint 3:
Planning:
Finish User Stories IS4, IS5, IS6, IS7, AS1(automation) By this sprint, the app should have individual pages for each student and each course along with the basic information like grade on the individual pages.
Task Assignment(tentative):
Omar: User Stories IS7, AS1(automation) make individual student report page
Hong: User Stories IS4, IS6, make individual course report page
Wei: User Story IS5, Create interactive elements/UI design on the main page and summary
Sprint 4:
Planning:
Finish User Stories IS8, IS9, feedback after first demo By this sprint, the app should have all of the necessary features of course data statistics and analysis, grade, quiz, demographics...dynamic UI, more interactive features on the from end, using javascript
and work on the document and add possible features with more
Task Assignment(tentative):
Omar: User Story IS8, do the charts for quizzes
Hong: User Story IS9, do the analysis for quizes
Wei: Create interactive elements/UI design on the newly created pages and documentation is assignment for every team member
Sprint 5:
Planning:
Finish optional User stories IS10, IS11, AS2 Debugging and testing, + feedback from second demo Also finish up documentation
Task Assignment(tentative):
Omar: AS2, testing, debugging and documentation
Hong: IS10, testing debugging and documentation
Wei: IS11, front end polish up and documentation