## 项目
Gannt Chart
[5 empty] | Planning |  | Real | % complete
| Strating | End | Percentage
Activities | Time | Time | Completed | Period
|  |  |  | Sprint 1 |  | Sprint 2 |  |  | Sprint 3 | Sprint 4 | Sprint 5 | Presentation
Sprint 1 | 9.15 | 9.26 | 100%
Sprint 2 | 9.26 | 10.17 | 5%
Sprint 3 | 10.17 | 11.04 | 0%
Sprint 4 | 11.04 | 11.21 | 0%
Sprint 5 | 11.21 | 12.02 | 0%
Presentation | 12.02 | 12.02 | 0%
Sprint 1: | Omar: Setting up Cybera server and Gantt Chart
Hong: User Stories, UML diagram and planning
Wei: UI and prototype Design and Storyboard
Sprint 2: | Omar: User Stories AS1, AS4, upload CSV file into Mysql and populate the database
Hong: User Stories IS1, IS2, IS3, set up database connection to backend with PHP
Wei: UI Design for the front end and help finish the user stories for this sprint
Sprint 3: | Omar: User Stories IS4, AS2, AS3, make individual student report page
Hong: User Stories IS6, IS11, make individual course report page
Wei: Create interactive elements/UI design on the web page for individual student and course
Sprint 4: | Omar: User Stories IS5, IS8, do the statistics and analysis for quizzes
Hong: User Stories IS7, IS10, do the statistics for forum and demographics
Wei: User Stories IS9, IS12, do the interactive charts for quizzes grades
and documentation is assignment for every team member
Sprint 5: | Omar: testing, debugging and documentation
Hong: testing debugging and documentation
Wei: front end polish up and documentation
Presentation: |  | All participate